## Slide 1: High Level Project Timeline
Sustain
&
Spread
Implement/
Control
Test
Changes
Develop/
Identify
Changes
Assess
  PROJECT TITLE
  Project Co-Leads:
  Sponsor: Champion: Oversight Committee:
  Improvement Advisor: Facility: Mentor:
{enter date range}
{enter date range}
{enter date range}
Assemble needed resources – Team Selection
Preliminary Process Map
Baseline Data Assessment
Root cause analysis
Draft project SMART goals
Draft Project ROI
Develop preliminary work plan
Develop data collection plan
Train Co-Leads and Team
Perform Project Kick-Off
Finalize SMART Goals
Map Process with Team
Identify Opportunities for Improvement:
Standardize and simplify
Reduce waste
Reduce defects
6S: Sort, Shine, Set in order, Standardize, Safety, Sustain
Apply evidence based practice
Find and improve the changes that solve the problem – run charts or control charts
Plan, Do, Study, Act:
Test by starting small (with just”1”)
Meet regularly to learn from previous cycle of testing and decide what to test next
Implement successful change(s) fully into system
Training/ On-boarding
Policy & Procedure
Job Aids
Feedback loops
Error Proofing
Develop Sustainability Plan with Co-Leads/Process Owners
Assist Co-Leads in taking ownership of metrics and processes
Consider “Spread” to other units/ departments/ medical centers/ regions as appropriate
{enter date range}
{enter date range}

## Slide 2: 90 – 120 Day Improvement Cycle
Point in Time | Team Activity
- 2 Weeks | Draft Project Charter with Co-Leads and Champion
Week 1 | Team Kick-Off – Finalize Project Charter
Week 2 | Define Measures
Week 3 | Gather Baseline Data and Create a Run Chart
Week 4 | Develop a Project Driver Diagram
Week 5 | Develop Current State Process Map
Week 6 | Identify and Prioritize Change Opportunities
Week 7 | Plan - PDSA #1 and PDSA #2
Week 8 | “Do” - PDSA #1
Week 9 | “Do” - PDSA #2
Week 10 | “Study” and Decide “Act” – PDSA #1
Week 11 | “Study” and Decide “Act” – PDSA #2
Week 12 | Hardwire PDSA’s and Monitor Progress
Week 13 | Develop Sustainability Plan
High Level Project Timeline – Another Example

## Slide 3
Project SMART Goal
Issues / Mitigation
Key Accomplishments / Decisions
Plans for Next Two Weeks
  BPMC Improvement Advisor Project:
  Improvement Advisor: Department: Biweekly Status Report:
Project Progress/Status
Project Phase [Assess-Develop-Test-Implement-Sustain-Spread]
Yellow
Red
Green